## Instructions
Dear Colleague, As you embark upon implementing mHero within a Ministry of Health, it is important to develop an implementation plan and to keep track of all of the various individuals and stakeholders with whom you will be working. This workbook provides you with a centralized location for managing both. The "Implementation Plan" tab provides a sample implementation plan that can be tailored to meet the needs of your project and the "mHero Stakeholders" tab contains a stakeholder matrix for managing your stakeholders and the frequency and ways in which you communicate with them.

## Implementation Plan
mHero Quarterly Country Operational Plan (INSERT TIME PERIOD)
# | Illustrative Activities | Lead | Remote Support Provided* | Month 1 (INSERT NAME OF MONTH) |  |  |  | Month 2 (INSERT NAME OF MONTH) |  |  |  | Month 3 (INSERT NAME OF MONTH)
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1 | mHero Ongoing Planning and Review
| Determine mHero Leadership Team to with representatives from communications, use case development, M&E, and other mHero teams | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Monthly Review of Implementation plan for planning of upcoming month | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Develop Quarterly Operational Plan for review and approval | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Sustainability Planning Meeting (to determine who will continue supporting mHero implementation) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
mHero Leadership Team Meeting (MONTHLY)
| Weekly mHero All Team Meeting - (at least one member from the Leadership Team attend if possible) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
2 | iHRIS and DHIS2 Integration
| Identify and engage HRIS team to mHero | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Obtain permission to remotely access HRIS database | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Obtain permission to routinely access Facility and Organization data (e.g. from DHIS2) from MOH | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Routinely engage with HRIS and DHIS2 teams to update HIS data | INSERT NAME OF TEAM/PERSON RESPONSIBLE
3 | Technical Installation of mHero
| Identification of mHero Technical Team and Resources | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| mHero Installation | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Create in country testing, headquarter testing and prodcution workspaces in RapidPro | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Obtain Android phone and install RapidPro application from Google Play store and configure it as SMS gateway for “In-Country Testing” workspace | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| mHero Adaptation with local HRIS | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Engagement with local Mobile Network Operators (in collaboration with UNICEF) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Finalize MNO Contracts | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| RapidPro Training for Workflow Development | INSERT NAME OF TEAM/PERSON RESPONSIBLE
4 | Coordination and Communication for mHero
| Establish communication and coordination team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Obtain official government endorsement of mHero | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Communicate with key district level staff/team on mHero | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Stakeholder Mapping | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Internal presentations and Awareness Raising of mHero platform | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Development of Standard Operating Procedures and Policy | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Internal communication management of Standard Operating Procedures | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Official launch of mHero (press release, meeting event) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
5 | Use Case Development
| Establish Use Case Development and Implementation Team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Identification of priority use cases | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Use Case Mapping (who will send messages; who will receive messages; who will analyze data) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Communicate use case needs with implementation team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Monthly Review of Use Case Priority List | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Ongoing communication with development team to support use case technical development | INSERT NAME OF TEAM/PERSON RESPONSIBLE
6 | Use Case Implementation (a separate tool can be used to track more detail for each use case with high level updates for the use case deployment included in the implementation plan)
| Develop workflow for Use Case #1 | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Egnagement with mHero Technical Team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Identify health workers to be contacted | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Test mHero workflow and make revisions via pilot | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Update use case based on pilot activity | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Identify timeline for use case rollout including follow up | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Formalize parties involved in use data analysis | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Intiate use case | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Update monitoring tools with use case data (ensure those who need the data have access to the information) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Ongoing follow up on use case activity | INSERT NAME OF TEAM/PERSON RESPONSIBLE
7 | Monitoring and Evaluation
| Develop M&E Team and determine roles and responsibilities | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Development of M&E Plan for mHero | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Identify analytical needs for measurement | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Develop and review monitoring forms | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Communicate mHero Results to mHero Leadership Team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Ongoing review of M&E Plan and Data | INSERT NAME OF TEAM/PERSON RESPONSIBLE
8 | Governance (suggest the mHero Leadership Team lead this area )
| Develop and Finalize Data Sharing Agreement on mHero with MOH (such agreement will inform policies supporting mHero) | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Draft Standard Operating Procedures for mHero | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Circulate for Review and Feedback | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Incorporate Feedback and Validate SoP | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Develop recommendations for integration of mHero to HRIS Policy | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| Develop recommendations for integration of mHero to HR Policy and Plan | INSERT NAME OF TEAM/PERSON RESPONSIBLE
9 | Other
| Identification of representatives from Other Units to join team | INSERT NAME OF TEAM/PERSON RESPONSIBLE
| mHero Trainings with national and district implementers to develop workflows and communicate with health workers | INSERT NAME OF TEAM/PERSON RESPONSIBLE
*Indicate with an "X" if this requiresparticipation and support from the IntraHealth or UNICEF teams based outside of the country. In planning your meetings and activities, please be sure you liaise with the appropriate technical and management staff at IntraHealth and UNICEF to ensure their availability to support the activity.

## mHero Stakeholders
Stakeholders Management and Information dissemination Plan for mHero
Illustrative Stakeholders | Location | Internal | Interest | Stake | Purpose | Capacity or Role | Level of influence on the project | Level of project impact on them | Information | Informat | Frequency
Or
(Name) | (Where and what they are or where and what he or she is?) | External | (What is the stakeholder’s interest in the project?) | (How is the stakeholder affected by the project?) | (What does the stakeholder need from the project, or what does the project need from the stakeholder?) | (What is the contribution of the stakeholder in project? Is it very strong, medium or weak) | (High, Medium or Low) | (High, Medium or Low) | (Information needed by stakeholder) | (Means of dissemination: e-mail, text, news letters, face-to-face meeting, etc.) | (Number of times information sharing is required with stakeholder)
Minister of Health | Opinion Leaders of Central MOH | Internal
Deputy for Health Services
Deputy for Planning & Research
Deputy for Administration
Assistant for Preventive Services
Assistant for Vital Statistics
County Health Officers | Opinion Leaders of County or District Health Teams
County's M&E Officer
mHero Team | MOH
Social Welfare |  | Internal
Minister of Finance | Opinion Leaders of Ministry of Finance | Internal
Deputy for Planning
Deputy for Finance
County or District Superintendents | Local Authorities and Civil Society Organizations | Internal
Development Superintendents
Local Traditional Leaders
Local Women Group
Local Community Mobilizers
Local Youth Groups
Christian Religious Groups | Faith-based Organizations | Internal
Islamic Religious Groups
Tradititional Religious Gps

## License Information
This information is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The contents are the responsibility of IntraHealth International and do not necessarily reflect the views of USAID or the United States Government.
© IntraHealth International. This document is made available under a Creative Commons Attribution-ShareAlike 4.0 International: https://creativecommons.org/licenses/by-sa/4.0/